|  | INF.17 |
| --- | --- |
| Economic Commission for Europe Inland Transport Committee Working Party on the Transport of Dangerous Goods Joint Meeting of Experts on the Regulations annexed to the European Agreement concerning the International Carriage of Dangerous Goods by Inland Waterways (ADN) (ADN Safety Committee) Twenty-first session Geneva, 27–31 August 2012 Item 10 of the provisional agenda Other business | 14 August 2012 |

UNECE Environment Division project on hazard and crisis management in the Danube Delta

Note by the secretariat

Information on a project carried out by the UNECE Environment Division which may be of interest to the ADN Safety Committee appears below. Further information on the elaboration of safety guidelines for oil terminals will be provided when available.

#### Background

The project on hazard and crisis management in the Danube Delta is carried out within the Assistance Programme of the UNECE Convention on the Transboundary Effects of Industrial Accidents. The Assistance Programme was launched in 2004 and aims at supporting Parties and ECE countries with economies in transition to improve industrial safety through the implementation of the Convention.

The general objective of the Danube Delta Project (DDP) is to improve the cooperation between the Republic of Moldova, Ukraine and Romania in the Danube Delta region through enhancing and, where possible, harmonizing the mechanisms and approaches for efficient and effective hazard and crisis management. The project started with preparatory meetings in December 2010. It is to be implemented over a three-year period according to the project implementation plan adopted during the kick-off meeting in May 2011 in Kyiv.

Project Objectives

Effective cooperation on industrial safety between the three countries can only be successful if it addresses both hazard management (prevention) and crisis management (preparedness and response). In order to improve the countries’ cooperation in hazard and crisis management in the Danube Delta region, the project should lead to the following results (specific objectives):

The establishment of a hazard spots map in the region of the Danube Delta with the hazards identified in a harmonized way;

The introduction of procedures for hazard notification, in particular for hazardous activities;

The development of practical recommendations/actions for national authorities to strengthen hazard and crisis management;

The improvement of cooperation between the authorities and the industry;

The harmonization of the facilities’ on- and off-site contingency plans ;

The harmonization of off-site contingency plans between the project countries through the establishment of a contingency plan for the Danube Delta;

The introduction of procedures for crisis notification and joint response; and

The strengthening of public awareness on hazard and crisis management.

Project Activities

In order to reach the project objectives, the three project countries agreed to carry out a number of specific activities included in the project implementation plan, in particular:

A technical workshop on hazard management in Chisinau, Republic of Moldova (July 2011);

A joint visit to the ports of Galati, Romania, and Giurgiulesti, Republic of Moldova (September 2011);

A technical workshop on crisis management in Chisinau, Republic of Moldova (December 2011);

The establishment of an expert group for the elaboration of safety guidelines for oil terminals (March 2012 to March 2013);

A second joint visit to the ports of Izmail and Reni, Ukraine (scheduled for May 2012);

A table-top exercise (scheduled for September 2012);

A second technical workshop on hazard management (scheduled for November 2012);

A field exercise (scheduled for April 2013);

A training for inspectors (scheduled for March 2013); and

A final project workshop (scheduled for June 2013).

_____________________