## Existing GTRs - High priority
Ia. Existing GTRs - High priority
GTR | Title | GR | Version | Reason | Organsiation of work | Reference documents | Expected time needed to finalise | Status
GTR 1 | Door locks & retention components | GRSP | Amendment 2 | Reflect UN Reg 11 | IWG: None Sponsor: None | AC.3/43 GRSP/2016/17 | 2017-06-01 | AC.3 endorsed the request of authorization to develop the amendment at its June 2016 session. For WP.29 vote in June 2017
GTR 3 | Motorcycle brake systems | GRRF | Amendment 3 | Reflect UN Reg 78 | IWG: None Sponsor: IT |  | 2018-03-01 | Draft request for authorization to develop Amendment 3 to UN GTR No. 3 for consideration by AC.3 in November 2016
GTR 7 | Head restraints | GRSP | Phase 2 | Amend UN Reg 17 (in parallel) | IWG: Yes (UK) Sponsor: JAP | AC.3/25/Rev.1 GRSP/2015/34 | End of 2018 | GRSP is expected to consider an informal proposal, addressing all issues, including draft Addendum 1 to the M.R.1 at its December 2016 session. AC.3 agreed to extend the mandate of the IWG until March 2017.
GTR 9 | Pedestrian safety | GRSP | Phase 2 | Improve harmonisation, increase safety | IWG: Yes (DE, JAP) Sponsor: DE, JAP | AC.3/24 2016/115 | Phase 2 (new leg form impactor) is finalised, waiting for US vote. Amendments to phase 1 and 2 (clarifications and bumper test zone) idem. The new work on deployable systems (by KOR, OICA for pop-up bonnets, external airbags, etc) still under development, to be finalized by end of 2017, but probably one more year needed. | GRSP will resume discussion at its December 2016 session on IARVs and on the draft UN GTR, altogether with a proposal addressing bumper test. AC.3 endorsed the authorization to develop an amendment to the UN GTR to provide the test procedure for deployable systems of the outer surface to ensure an adequate protection of pedestrians and extended the mandate of the IWG on Phase 2 until December 2017.
|  |  | Amendment 3 | Reflect UN Reg 127 | IWG: ??? Sponsor: EC | AC.3/31 GRSP/2014/2 GRSP/2014/5 | Done. This concerns phase 2 as well as the amendments to phase 1 and 2 which are already transposed into R127 | GRSP will consider a revised proposal concerning points of contact of headform impactors at its December 2016 session addressing the Phase 1 and 2 of the UN GTR.
GTR 11 | Test procedure for pollutant emissions in CI engines in tractors & NRMM | GRPE |  | Reflect amendments of UN Reg 96 |  |  |  | Work expected to start in 2018, after amendment of UN Reg 96 which is adapted to the new EU Regulation on NRMM (Stage V)
GTR 13 | GTR on Hydrogen & fuel cell vehciles | GRSP | Phase 2 |  |  |  | End of 2020 | PoW is expected to be finalized in the near future & an informal proposal of authorization to develop Phase 2 was endorsed by AC.3 in March 2017 session, AC3/49 for endorsement in June 2017 session
GTR 15 | World harmonised light vehicle test procedures (WLTP) | GRPE | Amendment 3 | Reflect EU legislation on WLTP |  |  |  | At the June 2017 GRPE conference, the AMENDMENT 3 has been adopted by GRPE, together with a further informal document providing further amendments to AMENDMENT 3. So the discussion on Amendment 2 might be pointless.
GTR 16 | Tyres | GRRF | Amendment 2 |  | IWG: Yes (RUS) Sponsor: RUS |  | 2018-11-01 | Draft request for authorization to develop Amendment 2 to UN GTR No. 16 for consideration by AC.3 in November 2016
GTR x1 | Evaporative emissions in passenger cars (WLTP EVAP) | GRPE | GTR (see comment in red) | Reflect EU legislation on WLTP | IWG: ??? (--) Sponsor: EU, JPN |  |  | Adoption of the new GTR at WP.29 June 2017 session; work will be carried on on sealed & semi-sealed tanks. Note that the sealed tanks have been included in the newly adopted (as informal document) EVAP GTR (June 2017 GRPE conference). Instead for the semi-sealed tanks the work will continue, with limited or no possibility to be concluded in time for the next GRPE conference in January 2018.
GTR x2 | Electrical Vehicle Safety (EVS) | GRSP | Phase 1 and Phase 2 |  | IWG: Yes (US, EU, JPN, CHN) Sponsor: US, EU, JPN, CHN | AC.3/32 |  | GRSP in May gave a green light to WP29 to proceed with a vote. Adoption of the new GTR is foreseen at WP.29 November 2017 session. Phase 2 (long-term research items) mandate expected to be approved by WP29 in November 2017.

## Existing GTRs - Low priority
Ib . Existing GTRs - Low priority
GTR | Title | GR | Version | Reason | Organsiation of work | Reference documents | Expected time needed to finalise* | Status
GTR 2 | Measurment procedures for 2-wheelers (WMTC) | GRPE | Amendment 4 |  | IWG: EPPR (SW) Sponsor: EU | AC.3/36 |  | AC.3 recommended, in March 2015, that the IWG continue to work on the creation of a new specific UN GTR.
GTR 4 | Test procedure gas-fuelled engines (WHDC) | GRPE | Amendment 4 |  |  |  |  | "There is need for extra validation of methodology regarding hybrids" - Please check
GTR 6 | Safety glazing materials vehicles & veh equipment | GRSG | ? |  | IWG: Yes (KOR, DE) Sponsor: KOR | AC.3/41 |  | AC.3 noted the request by GRSG to further update the Term of References and the need to extend the mandate of the IWG on PSG until June 2018. Awaiting technical investigation results
GTR 15 | World harmonised light vehicle test procedures (WLTP) | GRPE | n/a | Reflect EU legislation on WLTP | IWG: EVE (US, JPN, CHN) Sponsor: CAN, US, EU, JPN, CHN |  |  | Continue research on certain environmental requirements for electric vehicles. Awaiting input from WLTP phase2. For the moment the activities related to the electrified vehicles (determination of max power, battery durability, etc.) are still being dealt with mainly by the EVE IWG, which is external to WLTP. WHen and how this work will become an amendment to the GTR 15 or a separate GTR is still unclear.
| * | (in months)

## Existing GTRs - no activity
Ic. Existing GTRs - No activities identified for PoW
GTR | Title | GR | Version | Reason | Organsiation of work | Reference documents | Status
GTR 5 | Technical requirements for OBD systems | GRPE
GTR 8 | Electronic stability control | GRRF?
GTR 10 | Off-cycle emissions (OTC) | GRPE
GTR 12 | Motorcycle controls, tell-tales & indicators | GRE?
GTR 14 | Pole side impact (PSI) | GRSP |  |  | IWG: Yes (AUS) Sponsor: AUS |  | No new information was provided at the March 2016 session of AC.3.
GTR 17 | Crankcase and evaporative emissions of 2 or 3-wheeled motor vehicles | GRPE |  |  |  |  | Still to be notified!
GTR 18 | On-board diagnostics (OBD) for 2 or 3-wheeled motor vehicles | GRPE |  |  |  |  | Still to be notified!
GTR x3 | Quiet Road Transport Vehicles (QRTV) | GRB |  | Reflect UN Reg 138 | IWG: Yes (US); Vice-Chair JPN, Sec EC | GTR draft dated 19 Nov 2014 | Due to the effective date of US rule further extension to 5 September 2017, the US expert informed that the next QRTV GTR will be after that date. Further clarifications are expected to be addressed by NHTSA - USA in the WP29, June 201 session.

## New priorities
II. New Priorities
Title | Group | Organsiation of work | Reference documents | Time horizon for starting work* | Comments
Framework Regulation on automated/autonomous vehicles | New GR? ITS/AD? | (IWG ACSF) |  | MT (tbc) | Could possibly also take the form of a UNECE Regulation. [ACSF: Automatically Commanded Steering Function]
Cyber security | IG ITS/AD | TF CS/OTA |  | ST | It is not decided yet whether to regulate cyber security issues in ITS/AD IWG and TF. Could possibly also take the form of a UNECE Regulation. Work of Task Force on Cyber Security (CS) and Over-the-Air (OTA) updates is ongoing
Advanced Emergency Braking Systems (AEBS) | GRRF | IWG AEBS |  | MT (tbc) | Some work done on truck & bus collisions against moving and stationary obstacles (see UN Reg 131). Activity launched as an informal group on AEBS for cars (needed for the future revision of GSR)
Line Keeping Assist Systems (LKAS) | GRRF | (IWG ACSF) |  | MT (tbc) | WP29 aleady adopted an amendment to UN Regulation 79 in March 2017. This could be transformed into a GTR as US is also thinking about regulating.
Event Data Recorders (EDR) | GRSG? |  |  | MT (tbc) | Should be compatible with highly automated vehicle requirments.
Longitudinal control (ACC, preventive braking) | GRRF? |  |  | tbd | Could possibly also take the form of a UNECE Regulation. Longitudinal control not regulated today except AEBS for HDv
Driver availability recognition | ITS/AD?GRSG? |  |  | MT (tbc) | Should be compatible with highly automated vehicle requirments.
* | ST : Short Term (<1 year) - MT : Mid-term - LT : Long-term (>3 years)