## Slide 1: Status Report of the Informal Working Group on Safer Transport of Children in Buses and Coaches (IWG-STCBC)
Chair: Marta Anglès , SPAIN
Secretary: Costandinos VISVIKIS, CLEPA
Submitted by Spain
Informal document GRSG-127-15
(127th GRSG, 15–19 April 2024
Agenda item 2)

## Slide 2
Informal Working Group
      Lasts meeting
      19th IWG-STCBC meeting
      Date: 4th March 2024 Location: Online
      Next meeting
      20th IWG-STCBC meeting
      Date: 8th May 2024 Location: Helmond, Tass International

## Slide 3: Timeline
190
191
74
76
73
75
17
WP.29
GRSP
IWG
193
192
Informal Doc.
Plan and Schedule
189
1 2 3 4 5 6 7 8 9 10 11 12
2023
2024
2025
1 2 3 4 5 6 7 8 9 10 11 12
194
195
196
77
1 2 3 4 5 6 7 8 9 10 11 12
197
Working Doc.
18
19
20
21
22
23
24
25
2nd phase approved
IWG submission of 2nd phase Regulation

## Slide 4: Summary of the new UN Regulation
Time line | GRSP- May 2025 WP.29 – November 2025
Objective | No ejection of the children. Good retention in the seat
Phase 1 | a: CRS approved according to R-129 with 3-point belt and or ISOFIX b: Built in systems
Phase 2 | CRS in combination with 2-point belts

## Slide 5
      Test configurations: Frontal impact and rollover
      Retention system: 2-point belt
      Consideration of the CRS: R-129 approved CRS + additional new UN Regulation approval
UN R129
New
UN XXX
CRS for buses and coaches
Key Elements

## Slide 6
      Construction of the bus will not be modified.
      Separate components on the CRS for installation will not be allowed.
      Tests results:
          1st step: Dummy injury criteria for monitoring purposes only
          2nd step: Dummy injury criteria mandatory from 2027
Before 2027
Dummy injury criteria for monitoring purposes
Head displacement for monitoring purposes
After
2027
Dummy injury criteria mandatory
Head displacement mandatory
Decisions Done

## Slide 7
      Test procedure:
          Test bench (UN R129) / Real bus seat
      Labeling.
      Minimum characteristics necessary for the installation of the CRS in the bus seat:
          Length of Seat belt.
          Distance between lower anchorages points
          Length of the support leg
Ongoing

## Slide 8
Next Steps
      Tests comparison:
          Tests to be done in the UN R129 test bench
          Tests to be done in a bus seat with
      Workshop:
          Installation of CRS in the bus/coach.

## Slide 9: Thank you for your attention