# UN/SCEGHS/8/INF.39

COMMITTEE OF EXPERTS ON THE TRANSPORT OF

DANGEROUS GOODS AND ON THE GLOBALLY

HARMONIZED SYSTEM OF CLASSIFICATION

AND LABELLING OF CHEMICALS

# Sub-Committee of Experts on the Globally Harmonized

# System of Classification and Labelling of Chemicals

# (7 (p.m.)-9 December 2004)

COORDINATION AND WORK PROGRAMME

Programme of OECD Task Force for biennium 2005-2006

The purpose of this paper is to provide a draft proposal for a working plan on how the programme for work activities on Health and Environmental Hazards for updating of the Globally Harmonized System of Classification and Labelling of Chemicals during 2005-2006 to be undertaken by OECD Task Force may be detailed.

This draft proposal (see Table 1) lists the work activities, Sub-Committee mandate, working time-frames, expected scientific deliverables/outcomes and sub-activities so to clearly identify the working remit of the programme and ensure that work is maintained in a resource-effective manner.

The proposal may be further modified creating an additional document on work progress by identifying group experts from OECD, the Sub-Committees for GHS and TDG and industry, work events such as meetings and their dates, and progress reports/minutes on each stage of the work. Such a document may aid in co-ordinating, following the progress and increasing insight into the ongoing work for all  Parties.

| Table 1 . Work plan for OECD Task Force work activities for the 2005-2006 biennium |
| --- |
|  |  | Timeframe |  |  |
| Work activity | Mandate | Start | Complete | Deliverables | Sub-activities |
| Toxic Gas Mixtures | + | 2004 (ongoing) | end 2006 | - Validate formula - Proposal for criteria |  |
| Sensitization/induction/elicitation | + | 2003 | 2004 (delayed) | - Cut-off limits - Proposal for criteria |  |
| Sensitizers/strong vs. weak |  | 2003 | end 2006 | - Scientific issue paper |  |
| Cancer/potency | + | 2003 | end 2006 | - Scientific issue paper |  |
| Cancer/factors | + | 2003 | end 2006 | - Proposal for criteria |  |
| Reproduction/potency (cut-offs) | + | 2003 | December 2005 | - Scientific issue paper - Proposal for criteria |  |
| Chronic aquatic | + | 2003 | end 2006 | - Scientific issue paper |  |
| Transformation/Dissolution | + | 2003 | end 2006 | - Reliability (phase I) - Relevance (phase II) |  |
| Terrestrial environment | ? |  |  |  |  |
| Ozone Depleting Substances | ? |  |  |  |  |

# Footnotes

Pending discussion of UN/SCEGHS/8/INF.7

To be specified later

Reference and source of document identified or annexed

Has to be agreed by Sub-Committee. Expected to be completed December 2005

If agreed by Sub-Committee.

Dependent on available scientific information. Report to Sub-Committee, December 2005

Report to Sub-Committee, December 2005

Report to Sub-Committee, December 2005